Expected Project Work Packages (9. June – 22. December 2019):

- 1. WP June Paper and literature research, getting familiar with MATLAB code base and UWB firmware from Bitcraze
- 2. WP June Setting up the flying environment:
  - designing a mount for the drone-fixed tag module
  - constructing standing poles for the anchor modules
- 3. WP July Analyzing ranging capabilities of a tag/anchor pair
- 3. WP July Further developing the module firmware for setting the mode (TAG/ANCHOR) of the modules with an UWB message, allowing ranging between anchors and self-calibration of their positions
- 4. WP July Further developing the module firmware for receiving all ranging reports on the main computer over an additional connected module in SNIFFER mode
- 5. WP August Basic Gauss-Newton positioning with a handheld UWB tag as a proof of concept (Passing grade 4)
- 6. WP August Position control of the drone using a constant-velocity EKF
- 7. WP September Augmenting measurement model to accommodate for ranging offset orientation dependency
- 8. WP September Accuracy comparison with VICON ground-truth data:
  - EKF localization without offset correction
  - EKF localization with offset correction
- 9. WP October Outdoor flight testing
- 10. WP October Integrating GPS/Differential GPS sensor and report accuracy improvements
- 11. WP November-December Writing thesis and preparing presentation